## Burndown Chart Sprint1
First Sprint Burndown Chart
Task ID | Task Description | Initial Estimate time (Hours) | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | 1 day = 2/3 horas de trabalho max
1 | BPMN Register Account | 6 | 2025-09-30: 2; 2025-10-01: 1; 2025-10-02: 1; 2025-10-04: 2
2 | BPMN Post Content | 6 | 2025-10-01: 2; 2025-10-02: 3; 2025-10-03: 1 | NOTA: adicionar horas das tarefas das outras pessoas, fazer este preenchimento das horas na última reunião da semana
3 | BPMN Get Notifications | 6 | 2025-09-30: 3; 2025-10-01: 2; 2025-10-02: 1
4 | BPMN Adicionar Contacto | 6 | 2025-10-01: 2; 2025-10-02: 3; 2025-10-03: 1
5 | BPMN Send a Message | 6 | 2025-10-02: 2; 2025-10-03: 2; 2025-10-04: 2
6 | Frontend Adicionar User | 8 | 2025-10-08: 3; 2025-10-09: 3; 2025-10-10: 2
7 | Frontend Adicionar Contacto | 8 | 2025-10-15: 1; 2025-10-17: 3; 2025-10-18: 4
8 | Backend Adicionar User | 8 | 2025-10-07: 1; 2025-10-08: 2; 2025-10-09: 3; 2025-10-10: 2
9 | Backend Adicionar Contacto | 8 | 2025-10-16: 3; 2025-10-17: 3; 2025-10-18: 2
10 | BPMN Interact with Posts | 2 | 2025-10-07: 2
11 | BPMN Add Skill | 2 | 2025-10-06: 2
12 | BPMN Search Posts/People | 2 | 2025-10-07: 2
13 | BPMN Create and Reply to Listing | 2 | 2025-10-05: 2
14 | BPMN Create and Interact with Events | 2 | 2025-10-06: 2
15 | BPMN Create Groups | 2 | 2025-10-07: 2
16 | BPMN Discover Groups | 2 | 2025-10-05: 2
17 | BPMN AI Assistant | 2 | 2025-10-06: 2
18 | BPMN Post CV with anonymous reviews | 2 | 2025-10-06: 2
19 | BPMN Send GIFs in the comments | 2 | 2025-10-05: 2
20 | Functional Requirements – Task 2, 10, 11 | 6 | 2025-10-13: 2; 2025-10-14: 1; 2025-10-15: 2; 2025-10-16: 1
21 | Functional Requirements – Task 1, 16, 17 | 6 | 2025-10-17: 1; 2025-10-19: 2
22 | Functional Requirements – Task 3, 18, 19 | 6 | 2025-10-14: 1; 2025-10-15: 2; 2025-10-16: 1; 2025-10-19: 2
23 | Functional Requirements – Task 4, 12, 13 | 6 | bar: 2025-10-17 to 2025-10-18
24 | Functional Requirements da Task 5, 14, 15 | 6 | 2025-10-16: 1; 2025-10-17: 2
25 | Non-Functional Requirements | 2 | bar: 2025-10-18
26 | Frontend Enviar Mensagem | 6 | 2025-10-19: 2; 2025-10-20: 2
27 | Frontend Notificações | 6 | 2025-10-21: 2; 2025-10-22: 2
28 | Frontend Criar Post | 8 | bar: 2025-10-19 to 2025-10-20
29 | Backend Enviar Mensagem | 6 | 2025-10-19: 2; 2025-10-20: 1
30 | Backend Notificações | 6 | 2025-10-21: 1; 2025-10-22: 2
31 | Backend Criar Post | 8 | 2025-10-19: 1; 2025-10-20: 3; 2025-10-21: 2
32 | Criação do Gant Chart | 1 | bar: 2025-10-23
33 | BPMN Main Process | 3 | 2025-10-21: 1; 2025-10-22: 2
Completed Effort |  | 0 | 0 | 0 | 5 | 7 | 10 | 4 | 4 | 6 | 8 | 7 | 5 | 6 | 4 | 0 | 0 | 2 | 2 | 5 | 6 | 10 | 8 | 10 | 7 | 6 | 6 | 1 | 0 | 0 | 0
Remaining Effort |  | 158 | 158 | 158 | 153 | 146 | 136 | 132 | 128 | 122 | 114 | 107 | 102 | 96 | 92 | 92 | 92 | 90 | 88 | 83 | 77 | 67 | 59 | 49 | 42 | 36 | 30 | 29 | 29 | 29 | 29
Ideal Burndown |  | 158 | 152.5517 | 147.1034 | 141.6552 | 136.2069 | 130.7586 | 125.3103 | 119.8621 | 114.4138 | 108.9655 | 103.5172 | 98.069 | 92.6207 | 87.1724 | 81.7241 | 76.2759 | 70.8276 | 65.3793 | 59.931 | 54.4828 | 49.0345 | 43.5862 | 38.1379 | 32.6897 | 27.2414 | 21.7931 | 16.3448 | 10.8966 | 5.4483 | 0

## Burndown Chart s1
Semana1 Burndown Chart
Task ID | Task Description | Initial Estimate time (Hours) | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | 1 day = 2/3 horas de trabalho max
1 | BPMN Register Accout | 6 | 0 | 0 | 2 | 1 | 1 | 0 | 2
2 | BPMN Post Content | 6 | 0 | 0 | 0 | 2 | 3 | 1 | 0 | NOTA: adicionar horas das tarefas das outras pessoas, fazer este preenchimento das horas na última reunião da semana
3 | BPMN get notification | 6 | 0 | 0 | 3 | 2 | 1 | 0 | 0
4 | BPMN Adicionar Contacto | 6 | 0 | 0 | 0 | 2 | 3 | 1 | 0
5 | BPMN Send a Message | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Completed Effort |  | 0 | 0 | 0 | 5 | 7 | 10 | 4 | 4
Remaining Effort |  | 30 | 30 | 30 | 25 | 18 | 8 | 4 | 0
Ideal Burndown |  | 30 | 25.7143 | 21.4286 | 17.1429 | 12.8571 | 8.5714 | 4.2857 | 0

## Burndown Chart s2
Semana2 Burndown Chart
Task ID | Task Description | Initial Estimate time (Hours) | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
6 | Frontend Adicionar User | 8 |  |  |  | 3 | 3 | 2
7 | Frontend Adicionar Contacto | 8
8 | Backend Adicionar User | 8 |  |  | 1 | 2 | 3 | 2
9 | Backend Adicionar Contacto | 8
10 | BPMN interagir posts | 2 |  |  | 2
11 | BPMN colocar competências | 2 |  | 2
12 | BPMN pesquisar posts ou contas | 2 |  |  | 2
13 | BPMN create and reply listing | 2 | 2
14 | BPMN criar ver e interagir com eventos | 2 |  | 2
15 | BPMN criar grupos | 2 |  |  | 2
16 | BPMN Descobrir novos grupos | 2 | 2
17 | BPMN falar com AI… | 2 |  | 2
18 | BPMN fazer post do teu CV anonymous | 2 |  | 2
19 | BPMN mandar gif nos comentários | 2 | 2
Completed Effort |  | 0 | 6 | 8 | 7 | 5 | 6 | 4 | 0
Remaining Effort |  | 52 | 46 | 38 | 31 | 26 | 20 | 16 | 16
Ideal Burndown |  | 52 | 44.5714 | 37.1429 | 29.7143 | 22.2857 | 14.8571 | 7.4286 | 0

## Burndown Chart s3
Semana3 Burndown Chart
Task ID | Task Description | Initial Estimate time (Hours) | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
20 | Functional Requirements – Task 2, 10, 11 | 6 |  | 2 | 1 | 2 | 1
21 | Functional Requirements – Task 1, 16, 17 | 6 | [5 empty] | 1 | 2
22 | Functional Requirements – Task 3, 18, 19 | 6 |  |  | 1 | 2 | 1 |  | 2
23 | Functional Requirements – Task 4, 12, 13 | 6 | [5 empty] | 1 | 1
24 | Functional Requirements da Task 5, 14, 15 | 6 |  |  |  |  | 1 | 2
25 | Non-Functional Requirements | 2 | [6 empty] | 2
7 | Frontend Adicionar Contacto | 8 |  |  |  | 1 |  | 3 | 4
9 | Backend Adicionar Contacto | 8 |  |  |  |  | 3 | 3 | 2
Completed Effort |  | 0 | 0 | 2 | 2 | 5 | 6 | 10 | 13
Remaining Effort |  | 48 | 48 | 46 | 44 | 39 | 33 | 23 | 10
Ideal Burndown |  | 48 | 41.1429 | 34.2857 | 27.4286 | 20.5714 | 13.7143 | 6.8571 | 0

## Burndown Chart s4
Semana4 Burndown Chart
Task ID | Task Description | Initial Estimate time (Hours) | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
21 | Functional Requirements – Task 1, 16, 17 | 3
23 | Functional Requirements – Task 4, 12, 13 | 4
24 | Functional Requirements da Task 5, 14, 15 | 3
26 | Frontend Enviar Mensagem | 6
27 | Frontend Notificações | 6
28 | Frontend Criar Post | 8
29 | Backend Enviar Mensagem | 6
30 | Backend Notificações | 6
31 | Backend Criar Post | 8
32 | Criação do Gant Chart | 1
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Effort |  | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
Ideal Burndown |  | 51 | 43.7143 | 36.4286 | 29.1429 | 21.8571 | 14.5714 | 7.2857 | 0

## Task Dependecies
TASK DEPENDENCIES | [6 empty] | NOTA: Quero retificar o tempo que demoramos em cada tarefa, apesar de demorar uma semana tudo porque vamos fazendo as duas tarefas em simultâneo, deviamos por exemplo dizer que na semana 2 demoramos 3 dias a fazer o BPMN e depois os outros 4 dias a fazer a tarefa de começar a implementar
TaskID | Task Name | Dependecy | Duration (Days) | Responsável | Task Start | Task End
TECNOLOGIAS: react, node.js, supabase
1 | BPMN Register Account | - | 3 | Francisco Mendes | 2025-09-30 | 2025-10-02
2 | BPMN Post Content | - | 3 | Beatriz | 2025-10-01 | 2025-10-03 | NOTA: Chega colocar a duração e a data de inicio que o final da tarefa é preenchido automático
3 | BPMN Get Notifications | - | 3 | Vicente | 2025-09-30 | 2025-10-02
4 | BPMN Adicionar Contacto | - | 3 | Francisco Jorge | 2025-10-01 | 2025-10-03
5 | BPMN Send a Message | - | 3 | Daniel | 2025-10-02 | 2025-10-04
6 | Frontend Adicionar User | Task 1 | 6 | Vicente, Daniel | 2025-10-05 | 2025-10-10
7 | Frontend Adicionar Contacto | Task 4, 6 | 3 | Vicente, Daniel | 2025-10-16 | 2025-10-18
8 | Backend Adicionar User | Task 1 | 6 | Beatriz, Francisco Jorge, Francisco Mendes | 2025-10-05 | 2025-10-10
9 | Backend Adicionar Contacto | Task 4, 8 | 3 | Beatriz, Francisco Jorge, Francisco Mendes | 2025-10-15 | 2025-10-17
10 | BPMN Interact with Posts | - | 1 | Beatriz | 2025-10-07 | 2025-10-07
11 | BPMN Add Skill | - | 1 | Beatriz | 2025-10-06 | 2025-10-06
12 | BPMN Search Posts/People | - | 1 | Francisco Jorge | 2025-10-07 | 2025-10-07
13 | BPMN Create and Reply to Listing | - | 1 | Francisco Jorge | 2025-10-05 | 2025-10-05
14 | BPMN Create and Interact with Events | - | 1 | Daniel | 2025-10-06 | 2025-10-06
15 | BPMN Create Groups | - | 1 | Daniel | 2025-10-07 | 2025-10-07
16 | BPMN Discover Groups | - | 1 | Francisco Mendes | 2025-10-05 | 2025-10-05
17 | BPMN AI Assistant | - | 1 | Francisco Mendes | 2025-10-06 | 2025-10-06
18 | BPMN Post CV with anonymous reviews | - | 1 | Vicente | 2025-10-06 | 2025-10-06
19 | BPMN Send GIFs in the comments | - | 1 | Vicente | 2025-10-05 | 2025-10-05
20 | Functional Requirements da Task 2, 10, 11 | Task 2, 10, 11 | 3 | Beatriz | 2025-10-13 | 2025-10-15
21 | Functional Requirements da Task 1, 16, 17 | Task 1, 16, 17 | 3 | Francisco Mendes | 2025-10-17 | ##
22 | Functional Requirements da Task 3, 18, 19 | Task 3, 18, 19 | 3 | Vicente | 2025-10-14 | 2025-10-16
23 | Functional Requirements da Task 4, 12, 13 | Task 4, 12, 13 | 3 | Francisco Jorge |  | ##
24 | Functional Requirements da Task 5, 14, 15 | Task 5, 14, 15 | 3 | Daniel | 1900-01-15 | ##
25 | Non-Functional Requirements | - | 1 | Todos | 2025-10-18 | 2025-10-18
26 | Frontend Messages | Task 6, 7 | 3 | Vicente, Daniel | 2025-10-20 | 2025-10-22
27 | Frontend Notifications | - | 3 | Vicente, Daniel | 2025-10-22 | 2025-10-24
28 | Frontend Posts | Task 6 | 4 | Vicente, Daniel | 2025-10-23 | 2025-10-26
29 | Backend Messages | Task 8, 9 | 3 | Beatriz, Francisco Jorge, Francisco Mendes | 2025-10-22 | 2025-10-24
30 | Backend Notifications | - | 3 | Beatriz, Francisco Jorge, Francisco Mendes | 2025-10-20 | 2025-10-22
31 | Backend Posts | Task 6 | 4 | Beatriz, Francisco Jorge, Francisco Mendes | 2025-10-23 | 2025-10-26
32 | BPMN Main Process | - | 1 | Beatriz |  | 0
33 | Criação do Gant Chart | - | 1 | Todos | 2025-10-26 | 2025-10-26
Formulas:
Task End = [Task Start]+[Duration (Days)]-1

## Gant Chart
NOTA: Fazer baseado na tabela das task dependecies, podemos fazer no fim